## Flight Delay Testcases
|  |  | Date | 2022-11-18
|  |  | Team ID | PNT2022TMID36549
|  |  | Project Name | Project - Developing a Flight Delay Prediction Model using Machine Learning
|  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Commnets | TC for Automation(Y/N) | BUG ID | Executed By
PredictionPage_TC_OO1 | Functional | Home Page | Verify user is able to see the Prediction input page when user clicked on URL | Any Latest Browser | 1.Enter URL and click go 2.Verify if the Prediction input is fully displayed or not | Flask App | The Prediction input page should be displayed | Working as expected | Pass
PredictionPage_TC_OO2 | UI | Home Page | Verify the UI elements in Prediction page | Any Latest Browser | 1.Enter URL and click go 2.Verify Prediction page with below UI elements: a.Flight number b.Date in terms of month, day of month and day of week c.Origin and Destination dropdown d.Flight Timings e.Submit button | Flask App | Application should show below UI elements: a.Flight Number b.Date in terms of month, day of month and day of week c.Origin and Destination dropdown d.Flight Timings e.Submit button | Working as expected | Pass
PredictionPage_TC_OO3 | Functional | Home page | Verify user is able to enter the flight details properly | Any Latest Browser | 1.Enter URL and click go 2.Enter valid flight number 3.Enter Valid date in terms of month, day of month and day of week 4.Enter valid origin and destination 5.Enter valid flight timings 6.Click submit | Flight Number: 2610 Month: 1 Day of Month: 2 Day of Week: 6 Origin: ATL Destination: MSP Scheduled Dept Time: 1210 Actual Dept Time: 1231 Scheduled Arr Time: 1415 | User should navigate to result page and input details are recieved properly | Working as expected | Pass
PredictionPage_TC_OO4 | Functional | Home Page | Verify user is able to log into application with Invalid input | Any Latest Browser | 1.Enter URL and click go 2.Enter valid flight number 3.Enter Valid date in terms of month, day of month and day of week 4.Enter valid origin and destination 5.Enter valid flight timings 6.Click submit | Flight Number: 2610 Month: 1 Day of Month: 2 Day of Week: 6 Origin: MSP Destination: MSP Scheduled Dept Time: 1210 Actual Dept Time: 1231 Scheduled Arr Time: 1415 | Application should show 'origin and destination airport can't be same airport ' validation message. | Working as expected | Fail | The origin airport and the destination airport cannot be the same
PredictionPage_TC_OO5 | Functional | Home Page | Verify user is able to log into application with Invalid input | Any Latest Browser | 1.Enter URL and click go 2.Enter valid flight number 3.Enter Valid date in terms of month, day of month and day of week 4.Enter valid origin and destination 5.Enter valid flight timings 6.Click submit | Flight Number: 2610 Month: 14 Day of Month: 2 Day of Week: 6 Origin: ATL Destination: MSP Scheduled Dept Time: 1210 Actual Dept Time: 1231 Scheduled Arr Time: 1415 | Application should show 'month value can't be more than 12 ' validation message. | Working as expected | Fail | The month value can't be more than 12
ResultPage_TC_OO1 | UI | Result page | Verify user is able to view the predicted results | Any Latest Browser | 1.Enter URL and click go 2.Enter the correct input values 3.Click the submit button 4.View Results page | Flight Number: 2610 Month: 1 Day of Month: 2 Day of Week: 6 Origin: ATL Destination: MSP Scheduled Dept Time: 1210 Actual Dept Time: 1231 Scheduled Arr Time: 1415 | Application should show 'Flight is on time or Flight is delayed' message. | Working as expected | Pass

## Test Scearnios
Test Scenarios
1 | Verify user is able to see home page
2 | Verify user is able to input values or not?
3 | Verify user has entered the correct values or not?
4 | Verify user is able to view the result page